## Slide 1
novagentica
01 / 06
NOVAGENTICA · INTERNAL DECISION · 24 JUN 2026
The back office, on one vendor.
Decision: Deel.
HR · IT · EOR · Payroll · Recruiting · managed endpoint. One contract, across the 3→30 ramp (Jul 26 → Jun 28).
A type-1 call. Decided on the terms — not the price.

## Slide 2
I.
novagentica
02 / 06
THE DECISION
One question, decided.
DECISION
Sign Deel as the single managed back-office vendor — 2-year term, 3→30 ramp.
OWNER
Shiv. Felix owns the payroll go-live gate.
REVERSIBILITY
Type-1. Re-migrating payroll + identity + devices off one platform is expensive — decide deliberately.
DECIDE BY
Before Stage-1 onboarding (Jul 2026). Pre-signature is peak leverage.

## Slide 3
II.
novagentica
03 / 06
WHAT THE MODEL SAID
Price was a tie. The call wasn't about price.
2-YEAR COST
Deel €97.2k vs Rippling €96.4k — 0.9%. A tie, within model noise.
FX
Deel is USD-billed; Rippling EUR-native. The weak-EUR case swings ~€8k against Deel.
SCORECARD
Deel 3.85 · Rippling 4.05 — close, and it flips on small changes.
THEREFORE
Decided on terms and fit, not on cost.

## Slide 4
III.
novagentica
04 / 06
THE FORK
Why Deel, not Rippling.
RIPPLING
Held the auto-renewal clause. Does not lease IT devices. Leads the draft scorecard — but on points that tie.
DEEL
No auto-renewal + locked rate — leverage at renewal. Leases IT devices — no internal IT hire. The pre-registered tripwire chose it.
On an all-eggs bet, optionality beats a 0.2-point edge.

## Slide 5
IV.
novagentica
05 / 06
CONDITIONS OF SIGNATURE
What we accept — and how we de-risk it.
01
CONFIRM THE DE COUNTRY FEE
EOR may carry a mandatory entity fee. Know it, and budget it, before signing.
02
LOCK THE FX
Fixed-FX clause or a simple hedge — Deel bills in USD.
03
DE-RISK THE GO-LIVE
Named, proven implementation lead; a recovered-failure reference. Felix lived a failed Deel go-live.
04
PARALLEL PAYROLL
Two clean cycles before cutover. Never single-cut pay.
05
TERMS IN WRITING
No auto-renewal, data export + exit assistance, SLAs with credits, device-lease scope.

## Slide 6
novagentica
06 / 06
DECISION
Approved. Conditional.
Deel — sign once the conditions are met.
CEO REVIEW
Approve, conditional. Optionality preserved; execution risk owned.
CROSS-MODEL
Single-model GO (Claude). Genuine second-model review pending.
REOPEN IF
Rippling's refusal wasn't final, or the DE fee breaks the budget — before signature.
Decided on the terms. Not the price.